## Slide 1: Children and young people’s mental health and wellbeing
NEEDS ASSESSMENT ACTION PLAN
Bedford Borough
August 2019

## Slide 2
 | RECOMMENDATIONS FOR THE SYSTEM | Lead and timescale | When
SY1 | Mental health literacy needs to continue to be improved across the system, including raising awareness and breaking the stigma. Professionals from across the system including front line staff should be encouraged to access training and professional development opportunities, with a particular focus on those working with vulnerable children and young people. | Proposed lead: Local Safeguarding Children’s Board (Bedfordshire) – Sophie Adams / Phillipa Scott | Start Oct 2019
SY2B | Targeted prevention and early intervention for individuals at increased risk of poor mental health should remain a priority for the system, and this support should include a focus on early years and lower/primary schools. | Proposed Leads: Sue Harrison | 2019/ 20
SY3 | There needs to be up to date and easily accessible information for children, young people and their families as well as health, education and care professionals on how to promote mental wellbeing and how to access support if needed. | Proposed Lead: Sarah James / Amy White | 2019/20
SY4 | Opportunities for peer support for children, young people and their families should be expanded in schools and community settings. | Proposed Lead: Sacha Rymell/ ELFT / CVS | 2019/20

## Slide 3
 | RECOMMENDATIONS FOR THE SYSTEM CONTINUED | Lead | Timescale
SY5 | Ensure the forthcoming Mental Health School Team is fully aligned to the existing CAMHS School Teams, and compliments the existing pathways and relationships, including with the school nursing teams. | Proposed Lead: Bedfordshire CCG – Linda Willis | 2019/20
SY6B | Ensuring those nearing their 18th birthday receive the appropriate support and achieve good outcomes should continue to be a shared priority. Actions to support this include: working towards a flexible 0-25 pathway for mental health support sharing learning from transition evaluations, including outcomes and the experiences of young people and involving them in decision making strengthening flexible, multi-agency working through joint commissioning and improved use of the “all about me” document. | Proposed Leads Linda Willis ELFT Emilie (?) and Kaysie Conroy | TBC
SY7 | We need to get better at demonstrating that the voice of CYP is heard and that action has been taken to improve access to support for mental health and wellbeing | Proposed Leads: Jill Wall (?) | 

## Slide 4
 | RECOMMENDATIONS FOR SCHOOLS AND COLLEGES | Leads | Timescales
SC1 | Schools and colleges should continue to build pupil resilience through whole school approaches to mental wellbeing, including promoting teaching staff wellbeing. Where schools and colleges are not engaging with the local support and services that are available, this should be identified and addressed. | Peter Fraser | 2019/20
SC2 | Bullying is a risk factor for poor mental health. Schools and colleges should evaluate whether current anti-bullying policies and approaches (including measures to address online bullying) are effective and in line with evidence based practice. | Peter Fraser | 2019/20

## Slide 5
RECOMMENDATIONS FOR CHILD & ADOLESCENT MENTAL HEALTH SERVICES |  | Leads | Timescale
CA1 | There should be an audit of referrals to Child and Adolescent Mental Health Services (CAMHS) that are not seen by CAMHS but are not accepted and/ or signposted to alternative support. The audit should assess the effectiveness of signposting. The results of the audit should form the basis of agreed actions and processes to ensure that those not meeting CAMHS thresholds have timely access to appropriate support. | Lead: Hasna Delfeka (Public Health) and ELFT | Start: Sept 2019 End: tbc
CA2B | The impact of targeted training delivered by ELFT aimed at improving quality of referrals should be reviewed. Referral sources and rates of inappropriate and signposted referrals should be reported to BCCG to monitor and assess improvement. | Lead: Linda Willis Jo Meehan | Start: Sept 2019 and ongoing
CA3B | The data reported by East London NHS Foundation Trust (ELFT, the CAMHS provider) to Bedfordshire Clinical Commissioning Group (BCCG) should be developed to include reporting of referral reasons, and confirmed diagnosis / nature of caseloads. More transparent reporting of waiting times is needed, including internal waiting times. | Lead: Linda Willis Jo Meehan | 2019/2020